## Scope & Objectives
PROJECT CHARTER
Project Summary: | Ensure bike availability across Washington, DC locations by discovering existing usage data through years and leverage that data to lower operational costs associated with the unpredictable nature of bike availability.
Project Name: | Bike Share Project | Initiated Date: | 2021-10-26
Client Organization: | Bike-share technology company | Initiated By: | Client organization
Client Contact: | jspm@cmu.edu | Last Updated: | 2021-10-28
Project Start Date: | 2021-10-25 | Last Updated by: | Team 7
Project End Date: | 2021-12-03
Project Team: | Ziyan Xia, Woochan Lee, Yueni Wang | This is where you put your names - so there's one place for leadership to look and see - who's on this team?
Client Sponsor: | Jamie McGovern & Nicole Goodman
Client Business Owner: | Bike-share technology company
Key Stakeholders: | Bike-share technology company, Jamie McGovern
Scope & Objectives: | -ensure bike availability across their Washington, DC locations. -leverage existing usage usage data to lower operational costs associated with the unpredictable nature of bike availability. -Build a model to predict availability of bikes by station at any given future date/time based on historical information available. -Create a presentation for your client to understand the new model |  |  | I think this needs to be level-set and reviewed - the way it reads as written implies you're doing a think piece on going into a different business - but that's not what we're expecting in a a presentation (focused on #4 - predicting where the bikes are, which will be used to serve objective 5 - lower operational costs/increasing revenue). Re-think the angle on this and confirm in class what the main objective of this project is, and how will your finding of that objective be used. Concerned about how this is written that you're off to do research on labor markets, funding sources, and changes to the business model. Figure out where the bikes are (or rather, will be), first and foremost. I think this may be confounding background context on the company with the scope and objective on this project, perhaps.
Team Roles: | Cecilia Xia | Responsibilities: | Team lead / organize meetings, timelines
| Yueni Wang |  | Point of contact with client organization
| Woochan Lee |  | Organize and keep track of key documents
Key Dates & Milestones: | 2021-10-28 | First meeting | Construct project plan
| 10/28/2021-10/31/2021 | Individual EDA
| 11/01/2021-11/04/2021 | Finish status report1 and statistical model fitting&analysis
| 11/04/2021-11/11/2021 | Finish status report 2 and EDA presentation
| 11/12/2021-11/19/2021 | Furnish final deliverables and justify our findings
| 11/20/2021-11/28/2021 | Finish EDA presentation
| 11/29/2021-12/01/2021 | Finish final presentation for clients

## Project Plan
By using all for everything, you're missing the opportunity to get different people in front of owning deliverables at different times - you write plans like this, sooner or later you're going to have someone on your team who realizes they can coast and you will carry them, because they're not really responsible for anything
Task | Notes | Resources |  | Estimated Hours | Planned Due Date | Actual Hours | Date Complete | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Dec | Dec | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Background Research |  | All |  | 1.5 | 2021-10-29
Conduct Stakeholder Interview(Class Q&A) |  | All |  | 1.5 | 2021-11-01
Set working cadence for team | Meeting dates: Thursday and Sunday 1 hour sessions | All |  | 1.5 | 2021-10-28 | 0.5 | 2021-10-28
Document Understanding & Scope |  | All |  | 1 | 2021-10-29 | 0.5 | 2021-10-28
Document Requirements |  | All |  |  | 2021-10-29 | 0.5 | 2021-10-28
Draft Project Plan |  | All |  |  | 2021-10-29 | 0.5 | 2021-10-28
Confirm Plan/Understanding with Stakeholder |  | All |  | 1 | 2021-11-01
Injest Data | To start in the first week of November meetings | Woochan |  | 0.5 | 2021-10-31
Transform Data |  | All |  | 0.5 | 2021-10-31
Explore Data (Iterate) |  | All |  | 2 | 2021-10-31
Analysis/Vizualization (Iterate) |  | All |  | 2 | 2021-10-31
Deliver First Status Report |  | Yueni | How is this all? | 1 | 2021-11-04
Identify Story to Tell that addresses Client Ask | First edit of deliverable | All |  | 1 | 2021-11-07
Align on Direction by Team |  | All |  | 1 | 2021-11-07
Author Status Report |  | Yueni | How is this all? | 1 | 2021-11-07
Quality Assure Status Report |  | All | How is this all? | 0.5 | 2021-11-07
Deliver Second Project Status Report |  | Woochan | How is this all? | 2 | 2021-11-12
Review and Align Presentation (EDA) |  | All |  | 3 | 2021-11-12
Deliver EDA presentation |  | Cecilia | How is this all? | 5min | 2021-11-12
get the final dataset ready |  | Ceciia |  | 3h | 2021-11-23
data sampling and modelling |  | Cecilia |  | 5h | 2021-11-23
model comparison |  | All |  | 3h | 2021-11-24
select model results visualization |  | All |  | 5h | 2021-11-24
data processing code check |  | Cecilia, Yueni |  | 6h | 2021-11-25
Deliver Third Project Status Report |  | Cecilia | How is this all? | 1h | 2021-11-25
Clear our logic about the whole process |  | All |  | 2h | 2021-11-26
Review and Align Final Presentation |  | All |  | 5h | 2021-11-26
Submit Final Presentation Deliverables |  | Cecilia | How is this all? | 3min | 2021-11-30
Practice Presentation Delivery |  | All |  | 1h | 2021-11-30
Present Final Deliverables to Clients |  | All |  | 30min | 2021-12-01
Project Debrief |  | All |  | 0.5 | 2021-12-03

## Requirements & Assumptions
See Scope/Objective feedback
Functional / Business Requirements | Assumptions / Requirements
-ensure bike availability across their Washington, DC locations. | The data doesn't take into account reshuffling of bikes in stations. The reshuffling vans will make sure bikes are efficiently allocated
-leverage existing usage data to lower operational costs associated with the unpredictable nature of bike availability. | The starting number of bikes will be the number of bikes that came in at 00:00am (and didn't leave) on the initial start time of the dataset
-Build a model to predict availability of bikes by station at any given future date/time based on historical information available. | We also assume that 2020 data will be affected by COVID pandemic
Optimize and
Design a plan to maintain the model for the clients
-Create a presentation for your client to understand the new model
Does this assumption impact what you're doing? Maybe confirm assumptions after aligning scope What does 95% profitable mean? What does this mean? Uncontrolable? Predict how many bikes at a place & time Requirement - how is the model to be maintained?