## Slide 1
Bike Share Project– Team 7 (KaZAM) Status Report
Date: | Nov 19, 2021 | Overall Status:
Team: | Ziyan Xia, Woochan Lee, Yueni Wang | 
Project Description: | Ensure bike availability across Washington, DC locations by utilizing existing usage data through the years and leverage that data to lower operational costs associated with the unpredictable nature of bike availability.
Status Summary
After delivering our EDA slides and presentation, we have obtained a general idea on how the data was formatted and how we should continue processing our data and build the initial model. Now we have divided our work into final data processing, data-reclustring and first model building attempts including time series analysis and cluster analysis
Workstream: | Trend | Comments:
Final data processing |  | The modified dataset from our EDA will be further processed based on our final selection of station clusters. Outliers with large negative availabilities will be removed and data from two months of our choices will be selected
Clustering |  | In our EDA, the clustering methods still need to be improved to get a proper cluster of stations we will be working on.
Model fitting |  | Based on our finalized data, we plan to try time series analysis, cluster analysis and other possible analysis methods to build a reasonable model
Date | Recent Accomplishments & Updates:
17-Nov-2021 | Making sure our intuition of model building is right and getting the idea of removing outliers from finalized data
19-Nov-2021 | Starting model building and testing our initial model
Date | Issue: | Assigned To: | Due:
17-Nov | Data processing | Woochan | 19-Nov
18-Nov | Station clustering | Yueni | 19-Nov
19-Nov | Model building | All members | 19-Nov
18-Nov | Time series modeling | Cecilia | 19-Nov
Date | Upcoming High-Level Activities:
17--Nov-2021 | Dividing our work and discuss our model designing intuitions with Nicole
19-Nov-2021 | Doing our individual tasks described in workstream