## Control Sheet
Risk, Action items, Issues, and Decision Log (RAID)
Revision History |  |  |  | Reviewer
Version | Author | Date | Change Description | Approver
Updated Risks & Issues | Rosa | 2022-03-25
Solved Risks & Issues raised last week | Rosa | 2022-04-01 | Updates in blue color
Reviewers / Approvers
Role | Name | Date | Reviewer / Approver
Contents of the file
SN | Description |  | Excel sheet name
1 | Guidance |  | Guidance
2 | Risks |  | Risks
3 | Unplanned Actions |  | Unplanned Actions
4 | Issues |  | Issues

## Guidance
Risks, Action items, Issues, and Decisions log (RAID)
Guidance and Definitions
Guidance for Risk Action Issues Decisions Log Reporting
The document defines the Risks Actions items, Issues, and Decisions (RAID) in a searchable log The objective of RAID template is to • Identify, report, and manage issues on an ongoing basis • Identify, analyze, report and manage risks on an ongoing basis • Identify and manage unplanned actions which are not part of the project plan • Make the affected group aware of the issues, risks, actions, and decisions • Assign responsibility for actions Introduction & Instructions Risk: A risk is a future event which may adversely affect the project. (No). - in the spreadsheet should be prefixed with R1, R2 etc.,to distinguish the Risk Identifications details by Risks. Issue: An issue is a matter of concern on a project. (No). - in the spreadsheet should be prefixed with I1, I2 etc.,to distinguish the Risk Identifications details by Issues. Action: Action / Tasks which are unplanned and not part of the Project plan but completion of these actions are critical (required to be closed) for completion of the project. (No). - in the spreadsheet should be prefixed with UA1, UA2 etc.,to distinguish the Risk Identifications details by Unplanned Action. Decision: A record of decisions made, who was consulted, when and why.
Instructions: Column A - Status to be entered depending upon the Risk / Issue / Action is Open, On-Hold or Closed Column B - ID # is the serial no. Use R1 for Risk #1, I1 for Issue #1, U1 for Unplanned Action #1 Column C - Use this field to add Sub-Groups to the items for ease of sorting or assignment Column D - Risk / Action / Issue Name Column E - Describe the Risk / Action / Issue in detail Column F - Date when the Risk / Action / Issue was raised Column G - Raised By - Details of the team member who raised the issue Column H - Impact of the issue / risk / unplanned action (High, Medium, Low) Column K- Planned action to resolve the issue / risk / unplanned action Column L- Action Taken to close the issue / risk / unplanned action Column M- Owner responsible for completing the action Column N- Original Closure date to document originally targetted for closing the action Column O- Revised Closure date for closing the action Column P- Actual Closure date of action Column Q - Comments if any to be documented Status Key a. Green : Task is completed. Task is on target plan for completion. Task started on time b. Red : Plan date will be Open / Missed/ Task Due c. Amber: Task is On Hold Risks : Any risks that arise during the course of the project framework should be documented in this sheet Instructions : Refer Issues instruction notes. Unplanned Actions : Any unplanned actions during the course of the project should be documented in this sheet Instructions : Refer Issues instruction notes. Risk Identification: To capture all the risks during the Due Diligence,Transition Solution Design and Contract Stage

## Risks
Status | Risk ID# | Sub Project | Risk Name | Description of Risk | Date Raised | Raised By | Risk Impact | Probability | Overall Risk Classification | Planned Action to Mitigate Risk | Action Taken | Owner | Original Closure Date | Revised Closure Date | Actual Closure Date | Comments
|  | Delphi | Not satisfying progress | What we have done might not be satisfying for our client | 2022-03-25 | Rosa | 2 | 2 | 4 | Schedule meeting with Jacob 4/1/22 | Discussed with our faculty advisor what we have so far and what we should focus on next |  | 2022-04-01 | NA | 2022-04-01 | Our client said what we have done is aligned up with what he though but he gave some suggestions about our future work. We are more clear about what we are going to do next (clustering analysis, everyday station correlation, etc.).
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
RISK LOG
Date of Review:
Risk Impact can be classified as
1 - Low, 2 - Medium, 3 - High
Probability can be classified as:
1. Unlikely to occur, 2.Medium, 3.Probable
Overall Risk Classification is the product of Impact & Probability. Score :
1-2:Slight Risk (Green), 3-5:Significant Risk (Yellow), 6-9:Major/Max Risk (Red)

## Issues
Status | Issue ID# | Sub Project | Issue Name | Description of Issue | Date Raised | Raised By | Issue Impact | Planned Action to Resolve | Action Taken | Owner | Original Closure Date | Revised Closure Date | Actual Closure Date | Comments
|  | Delphi | Future directions | Not sure about whether what we did is what our client wants | 2022-03-25 | Rosa | Medium | Schedule meeting with Jacob 4/1/22 | Talked with faculty advisor and discussed what we had for not and what we should ask in the meeting with our client |  | 2022-04-01 |  | 2022-04-01 | Met wtih out client and faculty advisor on 4/01/2022 and showed them what we have done so far. Our client agreed with what we did and gave us some suggestions for future directions.
ISSUES LOG
Date of Review:
Issue Impact can be classified as
Low, Medium, High

## Actions
Status | Action ID# | Sub Project | Unplanned Action | Unplanned Action Description | Date Raised | Raised By | Action Impact | Action Taken | Owner | Original Closure Date | Revised Closure Date | Actual Closure Date | Comments
UNPLANNED ACTIONS
Date of Review:
Action Impact can be classified as
Low, Medium, High

## Decisions
Decision ID# | Description of Decision | Date Decided | Decided By | Consulted With | Informed | Comments
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30