## Project Charter
PROJECT CHARTER
Project Summary: | CMU Delphi group supports and advises the U.S. CDC’s community-driven COVID-19 forecasting effort by collecting Covid data across states. In this Delphi covid project, our aim is to investigate if two different data signals collected by Delphi group getting at the same concept agree with each other. By Identifying and implementing effective statistical methods,we investigate and provide insights into reasons for any detected disagreement.
Project Name: | Delphi Capstone | Initiated Date: | 2022-02-15
Client Organization: | Delphi Group | Initiated By: | Bhoomika Moorjani
Client Contact: | Jacob Bien | Last Updated: | 2022-03-17
Project Start Date: | 2022-02-15 | Last Updated by: | Rosa (Zixuan) Jin (updates in red)
Project End Date: | TBD
Project Team Members: | Anirban Chowdhury, April (Yueni) Wang, Bhoomika Moorjani, Manna (Xiangman) Zhao, Rosa (Zixuan) Jin | We did make this cell larger but I think in the submitted form it looked different
Client Sponsor: | Jacob Bien
Client Business Owner: | Delphi Group
Key Stakeholders: | Jacob Bien (Delphi Group representative), CDC (Funder of Delphi), Valerie Ventura (Faculty advisor), Jamie McGovern (Course instructor), Anirban Chowdhury (Team member), April (Yueni) Wang (Team member), Bhoomika Moorjani (Team member), Manna (Xiangman) Zhao (Team member), Rosa (Zixuan) Jin (Team member),
Scope & Objectives: | As a data analyzing team working with Delphi on this project, our main goal is to investigate whether two signals measuring the same aspect of covid 19 are in agreement. Our objectives is to identify and implement effective methods to determine how much these two data signals agree or disagree with each other. Approaches to be explored include exact numeric agreement, spatial/temporal correlations, rank correlation or Pearson correlation. We intend to do further research on effective methods on data segmented by region or time. If two signals disagree, we would investigate and provide insights into reasons for the disagreement with further research and explorations. Our project should support the main goal of the Delphi group, which is to improve the health, safety, and well-being of America with more precise prediction and data reflections on COVID data, to create the expertise, information, and tools that people and communities need to protect health of the general public. Therefore, our work products should be most effective as it needs to be consumable by an average person.
Resource Roles: | 1) Anirban Chowdhury | Responsibilities: | .Weekly meetings and status report .Data Visualization and Comparing .Reviewing deliverables | We picked two pairs of data signals: 1. Two variables measuring test positivity rate from different sources; 2. Sore throat cases vs Google search volume. Then, we splitted into 3 sub-groups. Rosa and Bhoomika work on the test positivity rate signals comparison. Ani and April work on the sore throat cases and Google search volume comparison. Manna works on looking for new pair of data signals that we can do later.
| 2) April (Yueni) Wang |  | .Weekly meetings and status report .Data Processing .Interpreting results
| 3) Bhoomika Moorjani |  | .Main point of contact .Data Processing .Developing deliverables for clients
| 4) Manna (Xiangman) Zhao |  | .Weekly meetings and progress updates .Data Visualization and Comparing .Additional testing
| 5) Rosa (Zixuan) Jin |  | .Weekly meetings and progress updates .Interpreting results .Reviewing deliverables
Key Dates & Milestones: | 2022-02-14 | Submit Project Preferences
| 2022-02-24 | Project Kick-off Presentation
| 2022-03-02 | Data Visualizations & Exploring methods
| 2022-03-14 | 1st Presentation to our class
| 2022-03-17 | Further investigation on Data Visualizations
| TBD | 2nd Presentation to our class
| TBD | Exploring possible reasons for disagreement
| 2022-04-22 | Finalizing presentation deck
| Starting 2/28/2022 | RAID, Status Report (36-612 Cadence Assignment)
| TBD | Final Pressentation - Client Present

## Project Plan
Task | Notes | Individual Resource Names | Estimated Hours | Planned Date | Actual Hours | Actual Date | time axis 2022-01-24 to 2022-05-06
Background Research | Research on Delphi group | Ani, April, Bhoomika, Manna, Rosa | 10 | 2022-02-19 | 10 | 2022-02-19 | bar: 2022-02-16 to 2022-02-18
Prepare Stakeholder Analysis | 612 HW 1 | Ani, April, Bhoomika, Manna, Rosa | 10 | 2022-02-21 | 7.5 | 2022-02-21 | bar: 2022-02-19 to 2022-02-21
Schedule Stakeholder Interview/Kick-off |  |  |  | NA | bar: 2022-02-20 to 2022-02-22
Conduct Stakeholder Interview | same as project presentation |  | 5 | 2022-02-02 | 5 | 2022-02-02 | bar: 2022-02-02
Define Requirements |  | Ani, April, Bhoomika, Manna, Rosa | 5 | 2022-02-25 |  | 2022-02-24 | bar: 2022-02-25 to 2022-02-26; 2022-02-28
Draft RACI | 612 HW 2 | Ani | 1 | 2022-02-28 | 1 | 2022-02-26 | bar: 2022-02-25
Document Requirements |  | Ani, April, Bhoomika, Manna, Rosa | 5 | 2022-02-28 | 5 | 2022-02-26 | bar: 2022-02-25
Draft Charter | 612 HW 2 | April, Rosa | 2 | 2022-02-28 | 2 | 2022-02-26 | bar: 2022-02-25
Confirm Understanding/Scope | Written in charter, validated with whole team | April, Rosa | 5 | 2022-02-28 |  | 2022-02-26 | bar: 2022-02-22 to 2022-02-25
Set working cadence for team | Weekly meeting schedule to be confirmed | Ani, April, Bhoomika, Manna, Rosa | 5 | 2022-02-28 | 1 | 2022-02-24 | bar: 2022-02-25
Set update cadence with client | Weekly meeting schedule to be confirmed | Bhoomika | 2 | 2022-03-03 | 1 | 2022-02-24 | bar: 2022-02-25
Define Approach |  | Ani, April, Bhoomika, Manna, Rosa | 5 | 2022-03-03 | 5 | bar: 2022-02-02
Set project plan | 612 HW 2 | Ani, Bhoomika, Manna | 6 | 2022-02-28 | 5 | 2022-02-26 | bar: 2022-02-23 to 2022-02-26
Prepare Kickoff-Playback |  | Ani, April, Bhoomika, Manna, Rosa | 10 | 2022-02-23 | 5 | 2022-02-23 | bar: 2022-02-22 to 2022-02-24
Present Kickoff-Playback |  | Ani, April, Bhoomika, Manna, Rosa | 5 | 2022-02-24 | 5 | 2022-02-24 | bar: 2022-02-24
Validate Approach w/Faculty Advisor |  |  | 5 | 2022-03-03 | 5 | bar: 2022-03-03
Provide Data | Data was already provided in R | Jacob Bien | 0 | NA | 0 | NA
Injest Data | Data was already provided in R | Ani, April, Bhoomika, Manna, Rosa | 0 | NA | 1
Clean Data | Data provided was already clean | Ani, April, Bhoomika, Manna, Rosa | 0 | NA | 0
Explore Data (Iterate) | Bhoomika and Rosa: Exploring Two different signals measuring test positivity rates, try different methods to see agreement, and investigate possible reasons for disagreement; Ani and April: sore throat cases vs Google search volume, try different methods to see agreement, and investigate possible reasons for disagreement; Manna: Exploring new combination of signals to be compared | Ani, April, Bhoomika, Manna, Rosa | 60 | 2022-04-08 | Break these out into lines by person - you're working in streams, you can apply the same methods to multiple signals, but there's no way it's going to line up as a consistent logged hours per stream or by person. Your other option is to start logging individual time sheets, with person, date, start/stop - if you think that's easier. | bar: 2022-02-27 to 2022-03-03; 2022-03-14 to 2022-03-19; 2022-03-21 to 2022-03-26; 2022-03-28 to 2022-04-02; 2022-04-04 to 2022-04-08
Visualize Data (Iterate) |  | Ani, April, Bhoomika, Manna, Rosa | 60 | 2022-04-08 | Break these out into lines by person - you're working in streams, you can apply the same methods to multiple signals, but there's no way it's going to line up as a consistent logged hours per stream or by person. Your other option is to start logging individual time sheets, with person, date, start/stop - if you think that's easier. | bar: 2022-02-27 to 2022-03-03; 2022-03-14 to 2022-03-19; 2022-03-21 to 2022-03-26; 2022-03-28 to 2022-04-02; 2022-04-04 to 2022-04-08
Model Data (Iterate) |  | Ani, April, Bhoomika, Manna, Rosa | 60 | 2022-04-08 | Also please start adding the lines for the report by section/person - you're starting that now, would like to get visibility to that effort and progress | bar: 2022-02-27 to 2022-03-03; 2022-03-14 to 2022-03-19; 2022-03-21 to 2022-03-26; 2022-03-28 to 2022-04-02; 2022-04-04 to 2022-04-08
QA / Code Review |  |  | 20 | 2022-04-15 | bar: 2022-04-15
Document Technical Work |  | Ani, April, Bhoomika, Manna, Rosa | 20 | 2022-04-22 | bar: 2022-04-22
Draft work products and findings |  | Ani, April, Bhoomika, Manna, Rosa | 50 | 2022-04-22 | bar: 2022-04-18 to 2022-04-22
Draft work product summary presentation |  | Ani, April, Bhoomika, Manna, Rosa | 50 | 2022-04-25 | bar: 2022-04-18 to 2022-04-23; 2022-04-25
Approve work products |  | Jacob Bien, Valerie Ventura | 10 | 2022-04-27 | bar: 2022-04-26 to 2022-04-27
Present summary presentation. |  | Ani, April, Bhoomika, Manna, Rosa | 50 | 2022-04-29 | bar: 2022-04-29
Deliver final modeling report |  | Ani, April, Bhoomika, Manna, Rosa | 40 | 2022-05-03 | bar: 2022-05-03
Deliver Weekly Status Report | Iterative deadlines with weekly updates | Ani, April, Bhoomika, Manna, Rosa | 5 | 2022-05-04 | bar: 2022-05-04
Log Timesheet |  | Ani, April, Bhoomika, Manna, Rosa | 5 | 2022-05-05 | bar: 2022-05-05
Final Presentation |  | Ani, April, Bhoomika, Manna, Rosa | 50 | TBD
Project Debrief |  | Ani, April, Bhoomika, Manna, Rosa | 10 | 2022-05-06 | bar: 2022-05-06
571

## RACI
| Project Team | Faculty Advisor | Course Instructors | Client | [Add as needed]
High Level Project Activities | [5 empty] | Fill in with one of the following: R, A, C, I, [blank]
Understand Scope | R | A | I | C |  | Responsible for executing the task
Prepare Stakeholder Analysis | R | I | I | [blank] |  | Accountible for making decisions regarding the task
Schedule Stakeholder Interview/Facilitate Kickoff |  | A | [blank] | C |  | Consulted and must be part of decisions regarding the task
Define Requirements | I | I | R | C |  | Informed and must be told decisions and task status/outcome
Document Requirements | R | I | I | [blank] |  | [blank] - not involved in the task or decision
Prepare Kick-off Summary Presentation | R | C | [blank] | [blank]
Confirm Understanding/Scope | R | A | [blank] | C
Set working cadence for team | R | I | [blank] | [blank]
Set update cadence with client | R | C | [blank] | C
Define Approach | R | A | I | C
Set project plan | R | C | A | I
Provide Data | C | I | I | R
Ingest Data | R | C | I | I
Clean Data | R | C | I | I
Explore Data (Iterate) | R | C | I | I
Visualize Data (Iterate) | R | C | I | I
Model Data (Iterate) | R | C | I | I
QA / Code Review | R | C | I | I
Document Technical Work | R | C | I | C
Draft work products and findings | R | C | I | C
Draft work product summary presentation | R | C | I | C
Approve work products | I | C | I | R
Present summary presentation. | R | C | I | C