## Slide 1
Project Delphi Capstone – Status Report
Date: | 4/15/2022 | Overall Status:
Team: | Anirban Chowdhury, April (Yueni) Wang, Bhoomika Moorjani, Manna (Xiangman) Zhao, Rosa (Zixuan) Jin | 
Project Description: | Our aim is to investigate if two different data signals from Delphi group getting at the same concept agree and provide insights into reasons for detected disagreement.
Status Summary
Given our last meeting with our faculty advisor and client, we fixed what we have done based on their suggestions (moving average rank correlation) and used new methods to approach our project (clustering analysis, rank correlation over time, etc.). Calculated the mean test positivity rate for each state using the weighted average based on each county’s population and test positivity rate.
Workstream: | Trend | Comments:
Fixing what we did given the feedback from our client and faculty advisor |  | We fixed what we have done over the past weeks. For example, we plotted a moving average rank correlation for 5 states instead of plotting a monthly rank correlation.
New perspectives / method to approach our project |  | We used new methods to look at the rank correlations between two data signals: calculated rank correlation for each single day over time; did clustering analysis among the states using rank correlation, number of observations, and etc.
Date | Recent Accomplishments & Updates:
4/15/2022 | Group meeting - progress update, discussions about future directions & final presentation
4/15/2022 | Meeting with faculty advisor - progress updated, discussions about next steps Scheduling final presentation
Date | Issue: | Assigned To: | Due:
3/25/2022 | We plan to analyze these signals by county and explore possible demographic reasons for the disagreement. | Ani, April | 3/30/2022
4/05/2022 | Created moving average window and plotted moving average rank correlation for 5 states; calculated and plotted rank correlation across 50 states for each single day We plan on doing cluster analysis to identify states with similar trend in test positivity rate | Bhoomika, Rosa | 4/15/2022 4/22/2022
4/05/2022 | Calculated the rank correlation between two signals for six populous states based on 30-day moving window. Plot the rank correlation between two signals on 50 states on each fixed date to investigate the agreement rate from a new perspective. | Manna | 4/15/2022
4/1/22 | Experiment with Cluster analysis as raised by Jacob Bien in 4/1 Meeting in order to discern a different aspect of the correlation over space. | Ani | 4/12/22
Date | Upcoming High-Level Activities:
4/15/2022 | Group Meeting
4/15/2022 | Meeting with our faculty advisor
4/15/2022 | Submit revised 36726 assertion evidence slides
2/2/2022 - 6/2/2022 | Final Presentation
Updated by: Rosa (in red), Ani (in blue), Manna (in green), April (in pink), Bhoomika (in orange)